## CFA_Sprint
| Start Date |  | End Date |  |  |  |  | Meeting Type |  | No.Of Days | Duration | Total Hours
Sprint-1 | 2026-01-07 |  | 2026-01-20 |  | 1-Holiday |  |  | VL Standup(Weekly Twice)(Mor) |  | 04-Days | 15-Mins | 1-Hour
[8 empty] | CFA Standup (Daily) |  | 10-Days | 15-Mins | 2.5 -Hours
[8 empty] | CFA Sprint Planning & Refinement |  | 01-Days | 2-Hours | 2-Hours
[8 empty] | CFA Retro |  | 01-Days | 1-Hour | 1-Hour
[8 empty] | Unexpected Meetings |  | 1-Sprint | 1-Hour | 1-Hour
[12 empty] | 7.5-Hours | 2 SP
1-Sprint |  | 2-Weeks
1-Story Point |  | 4-Hours
| Total Working Days |  | Total SP | Leaves | Working Hours | Meetings(Hrs) | Available (Hrs) |  | Available SP | Expecting Utilize SP | Balance SP
Srikanth | 9 |  | 18 | 0 | 72 | 7.5 | 64.5 |  | 16.125 | 13 | 3.125
Subha | 9 |  | 18 | 0 | 72 | 7.5 | 64.5 |  | 16.125 | 13 | 3.125
Abhi | 9 |  | 18 | 0 | 72 | 7.5 | 64.5 |  | 16.125 | 13 | 3.125