## CFA_Sprint-2
| Start Date |  | End Date |  |  |  |  | Meeting Type |  | No.Of Days | Duration | Total Hours
Sprint-1 | 2025-03-19 |  | 2025-04-01 |  | 1-Holiday |  |  | VL Standup(Weekly Twice)(Mor) |  | 04-Days | 15-Mins | 1-Hour
Sprint-2 | 2025-04-02 |  | 2025-04-15 |  | No Holiday |  |  | VL Standup (Evening Daily) |  | 10-Days | 15-Mins | 2.5 -Hours
Sprint-3 | 2025-04-16 |  | 2025-04-29 |  | No Holiday |  |  | CFA Standup (Daily) |  | 10-Days | 15-Mins | 2.5 -Hours
Sprint-4 | 2025-04-30 |  | 2025-05-13 |  | 1-Holiday |  |  | CFA Sprint Planning & Refinement |  | 01-Days | 2-Hours | 2-Hours
Sprint-5 | 2025-05-14 |  | 2025-05-27 |  | No Holiday |  |  | CFA Retro |  | 01-Days | 1-Hour | 1-Hour
[8 empty] | Unexpected Meetings |  | 1-Sprint | 1-Hour | 1-Hour
[12 empty] | 10-Hours | 2.5 SP
1-Sprint |  | 2-Weeks
1-Story Point |  | 4-Hours | [5 empty] | NEXT Standup (Daily) |  | 10-Days | 15-Mins | 2.5 -Hours
[8 empty] | NEXT Sprint Planning & Refinement |  | 1-Day | 2-Hours | 2-Hours
[8 empty] | NEXT Retro |  | 1-Day | 1-Hour | 1-Hour
[12 empty] | 5.5-Hours | 1.4 SP
| Total Working Days |  | Total SP | Leaves | Working Hours | Meetings(Hrs) | Available (Hrs) |  | Available SP
Srikanth | 10 |  | 20 | 0 | 80 | 15.5 | 64.5 |  | 16.125
Santhosh | 10 |  | 20 | 1 | 72 | 10 | 62 |  | 15.5
Subha | 10 |  | 20 | 0 | 80 | 10 | 70 |  | 17.5
Abhi | 10 |  | 20 | 0 | 80 | 8 | 72 |  | 18
Prabhu | 10 |  | 20 | 0 | 80 | 7.5 | 72.5 |  | 18.125
Nitin | 10 |  | 20 | 1 | 72 | 7.5 | 64.5 |  | 16.125
Vivek | 10 |  | 20 | 0 | 80 | 7.5 | 72.5 |  | 18.125

## CFA_Sprint-1
| Start Date |  | End Date |  |  |  |  | Meeting Type |  | No.Of Days | Duration | Total Hours
Sprint-1 | 2025-03-19 |  | 2025-04-01 |  | 1-Holiday |  |  | VL Standup(Weekly Twice)(Mor) |  | 04-Days | 15-Mins | 1-Hour
Sprint-2 | 2025-04-02 |  | 2025-04-15 |  | No Holiday |  |  | VL Standup (Evening Daily) |  | 10-Days | 15-Mins | 2.5 -Hours
Sprint-3 | 2025-04-16 |  | 2025-04-29 |  | No Holiday |  |  | CFA Standup (Daily) |  | 10-Days | 15-Mins | 2.5 -Hours
Sprint-4 | 2025-04-30 |  | 2025-05-13 |  | 1-Holiday |  |  | CFA Sprint Planning & Refinement |  | 01-Days | 2-Hours | 2-Hours
Sprint-5 | 2025-05-14 |  | 2025-05-27 |  | No Holiday |  |  | CFA Retro |  | 01-Days | 1-Hour | 1-Hour
[8 empty] | Unexpected Meetings |  | 1-Sprint | 1-Hour | 1-Hour
[12 empty] | 10-Hours | 2.5 SP
1-Sprint |  | 2-Weeks
1-Story Point |  | 4-Hours | [5 empty] | NEXT Standup (Daily) |  | 10-Days | 15-Mins | 2.5 -Hours
[8 empty] | NEXT Sprint Planning & Refinement |  | 1-Day | 2-Hours | 2-Hours
[8 empty] | NEXT Retro |  | 1-Day | 1-Hour | 1-Hour
[12 empty] | 5.5-Hours | 1.4 SP
| Total Working Days |  | Total SP | Leaves | Working Hours | Meetings(Hrs) | Available (Hrs) |  | Available SP
Srikanth | 9 |  | 18 | 1 | 64 | 15.5 | 48.5 |  | 12.125
Santhosh | 9 |  | 18 | 0 | 72 | 10 | 62 |  | 15.5
Subha | 9 |  | 18 | 0 | 72 | 10 | 62 |  | 15.5
Abhi | 9 |  | 18 | 0 | 72 | 8 | 64 |  | 16
Prabhu | 9 |  | 18 | 0 | 72 | 7.5 | 64.5 |  | 16.125
Nitin | 9 |  | 18 | 1 | 64 | 7.5 | 56.5 |  | 14.125
Vivek | 9 |  | 18 | 0 | 72 | 7.5 | 64.5 |  | 16.125

## ZEUS_Sprint-1
| Sprint No | Start Date | End Date | Holiday |  |  |  | Meeting Type | Duration | No. Of Days | Total Hours | Total Story Points
| Sprint-1 | 2025-03-19 | 2025-04-01 | 2025-03-31 |  | 1SP | 4 Hrs | VL Standup (Weekly Twice)(Mor) | 15 Mins | 4 | 1 | 0.25
| Sprint-2 | 2025-04-02 | 2025-04-15 |  |  | 1 Sprint | 18 SP | VL Standup (Weekly Twice)(Eve)(QA) | 15 Mins | 4 | 1 | 0.25
| Sprint-3 | 2025-04-16 | 2025-04-29 |  |  |  |  | VL QA connect with Cameron( Weekly Once) (Eve) | 30 Mins | 2 | 1 | 0.25
| Sprint-4 | 2025-04-30 | 2025-05-13 |  |  |  |  | Hema Bi-Weekly connect with Cameron (Eve) | 15 Mins | 1 | 15 Mins
| Sprint-5 | 2025-05-14 | 2025-05-27 |  |  |  |  | Zeus onsite standup (Daily) | 30 Mins | 10 | 5 | 1.25
[8 empty] | Zeus Retro & Sprint Planning (Once in a sprint) | 1 Hr | 1 | 1 | 0.25
[8 empty] | Zeus Office Hours (Weekly twice) | 30 Mins | 4 | 2 | 0.5
[8 empty] | Zeus Technical Backlog Discussion (Weekly once) | 1 Hr | 2 | 2 | 0.5
[8 empty] | Unexpected Meetings | 1 Hr | 1 | 1 | 0.25
[8 empty] | Total |  |  | 14 | 3.5
| Total Working Days | Total SP | Leaves | WSP(hrs) | Meetings(hrs) | Available (hrs) | Available SP
Hema | 9 | 18 | 0 | 72 | 14 | 58 | 14.5 | Triton Walkthrough | 1.5 Hrs | 1 | 1.5 Hrs
Ramya | 9 | 18 | 0 | 72 | 14 | 58 | 14.5 | Improve Refinement | 30 Mins | 1 | 30 Mins
Priya | 9 | 18 | 0 | 72 | 14 | 58 | 14.5
[6 empty] | 174 | 43.5

## MERLIN_Sprint-1
Sprint No | Start Date | End Date | Holiday |  |  | Meeting Type |  | Duration | No. Of Days | Total Hours | Total Story Points
Sprint-1 | 2025-03-19 | 2025-04-01 | 2025-03-31 |  |  | VL Standup (Weekly Twice)(Mor) |  | 15 Mins | 4 | 1 | 0.25
Sprint-2 | 2025-04-02 | 2025-04-15 |  |  |  | VL Standup (Weekly Twice)(Eve) (QA) |  | 15 Mins | 4 | 1 | 0.25
Sprint-3 | 2025-04-16 | 2025-04-29 |  |  |  | VL QA connect with Cameron( Weekly Once) (Eve) (QA) |  | 30 Mins | 2 | 1 | 0.25
Sprint-4 | 2025-04-30 | 2025-05-13 |  |  |  | Merlin onsite standup (Daily) |  | 30 Mins | 10 | 5 | 1.25
Sprint-5 | 2025-05-14 | 2025-05-27 |  |  |  | Merlin Retro & Sprint Discussion (Once in a sprint) |  | 1 Hr | 1 | 1 | 0.25
[6 empty] | Merlin Office Hours (Weekly once) |  | 1 Hr | 2 | 2 | 0.5
[6 empty] | Merlin Technical Backlog Discussion (Weekly once) |  | 1 Hr | 2 | 2 | 0.5
[6 empty] | Unexpected Meetings |  | 1 Hr | 1 | 1 | 0.25
[6 empty] | Total |  |  |  | 14 | 3.5
Sprint-1
Name | Total Working Days | Total SP | Leaves | WSP(hrs) | Meetings(hrs) | Available (hrs) | Available SP
Vimala | 9 | 18 | 0 | 72 | 14 | 58 | 14.5
Sathish | 9 | 18 | 0 | 72 | 14 | 58 | 14.5
Manas | 9 | 18 | 0 | 72 | 12 | 60 | 15
Total | [5 empty] | 176 | 44
1 Sprint => 2 Weeks
1 Stpry Point (SP) => 4 Hrs

## ATLAS_Sprint-1
| Start Date |  | End Date |  |  |  |  | Meeting Type |  | No.Of Days | Duration | Total Hours
Sprint-1 | 2025-03-19 |  | 2025-04-01 |  | 1-Holiday |  |  | VL Standup(Weekly Twice)(Mor) |  | 04-Days | 15-Mins | 1-Hour
Sprint-2 | 2025-04-02 |  | 2025-04-15 |  | No Holiday |  |  | ATLAS Standup (Daily) |  | 10-Days | 15-Mins | 2.5 -Hours
Sprint-3 | 2025-04-16 |  | 2025-04-29 |  | No Holiday |  |  | Engineering hours |  | 10-Days | 30-Mins | 5 -Hours
Sprint-4 | 2025-04-30 |  | 2025-05-13 |  | 1-Holiday |  |  | Sprint Planning & Refinement |  | 01-Days | 2-Hours | 2-Hours
Sprint-5 | 2025-05-14 |  | 2025-05-27 |  | No Holiday |  |  | ATLAS Retro |  | 01-Days | 1-Hour | 1-Hour
[8 empty] | Unexpected Meetings |  | 1-Sprint | 1-Hour | 1-Hour
12.5-Hours
1-Sprint |  | 2-Weeks
1-Story Point |  | 4-Hours
| Total Working Days |  | Total SP | Leaves | Working Hours | Meetings(Hrs) | Available (Hrs) |  | Available SP
DINESH | 9 |  | 18 | 0 | 72 | 12.5 | 59.5 |  | 14.875
RAHUL | 9 |  | 18 | 0 | 72 | 12.5 | 59.5 |  | 14.875
ABHIMANYU | 9 |  | 18 | 0 | 72 | 8 | 64 |  | 16